## BondProjectSchoolFinance
KANSAS STATE DEPARTMENT OF EDUCATION
SCHOOL FINANCE REPORT
BOND PROCEEDS - BY PROJECT FOR 2010-11 SCHOOL YEAR
USD# | USD NAME | COUNTY NAME | NAME OF PROJECT | ESTIMATED COST | ACTUAL COST | STARTING DATE | COMPLETION DATE
D0101 | Erie-Galesburg | Neosho | Erie High School | 20600000 | 20600000 | 05-12-2008 | 07-18-2010
| Erie-Galesburg | Neosho | Galesburg Middle School | 1300000 | 1300000 | 05-12-2008 | 07-12-2010
|  |  | Total for D0101 | 21900000 | 21900000
D0113 | Prairie Hills | Nemaha | Sabetha/Wetmore facilities project | 9345000 | 6845000 | 10-01-2010 | 06-30-2011
|  |  | Total for D0113 | 9345000 | 6845000
D0200 | Greeley County Schools | Greeley | Elementary Remodel | 4810000 | 4810000 | 01-01-2011 | 06-30-2011
|  |  | Total for D0200 | 4810000 | 4810000
D0210 | Hugoton Public Schools | Stevens | Early Childhood Development Center | 5009885 | 4947490 | 11-01-2009 | 11-01-2010
| Hugoton Public Schools | Stevens | Middle School Addition | 5788581 | 5726131 | 11-01-2009 | 10-01-2010
| Hugoton Public Schools | Stevens | Link Addition | 5288441 | 5250186 | 11-01-2009 | 01-01-2011
| Hugoton Public Schools | Stevens | High School Athletic Complex | 3305550 | 3375761 | 11-01-2009 | 03-20-2011
|  |  | Total for D0210 | 19392457 | 19299568
D0229 | Blue Valley | Johnson | Blue Valley Southwest | 81543920 | 80634698 | 03-19-2008 | 08-18-2010
|  |  | Total for D0229 | 81543920 | 80634698
D0232 | De Soto | Johnson | Mill Valley High School Addition II | 17000000 | 17567301 | 08-01-2009 | 08-01-2010
| De Soto | Johnson | Belmont Elementary | 20000000 | 18040212 | 08-01-2009 | 08-01-2010
| De Soto | Johnson | De Soto High School Phase I | 4100000 | 3910202 | 10-01-2009 | 08-01-2010
| De Soto | Johnson | Video Surveillance | 1000000 | 1068810 | 07-01-2010 | 06-01-2011
|  |  | Total for D0232 | 42100000 | 40586525
D0259 | Wichita | Sedgwick | Clark Elementary | 767175 | 514921 | 12-02-2009 | 08-02-2010
| Wichita | Sedgwick | Cleaveland Elementary | 414100 | 274795 | 12-23-2009 | 09-07-2010
| Wichita | Sedgwick | Cloud Elementary | 1342725 | 1092168 | 12-23-2009 | 01-03-2011
| Wichita | Sedgwick | Linwood Elementary | 2184938 | 1908178 | 01-25-2010 | 10-19-2010
|  |  | Total for D0259 | 4708938 | 3790062
D0262 | Valley Center Pub Sch | Sedgwick | Athletic Improvements | 3491593 |  | 02-06-2009
| Valley Center Pub Sch | Sedgwick | Abilene Remodel/Rennovation | 1812549 | 1812549 | 03-06-2009 | 08-31-2010
| Valley Center Pub Sch | Sedgwick | West Remodel/Rennovation | 1725653 | 1725653 | 03-06-2009 | 07-31-2010
| Valley Center Pub Sch | Sedgwick | New High School | 42850000 |  | 05-21-2009
| Valley Center Pub Sch | Sedgwick | Technology Improvements | 3000000 |  | 06-11-2009
| Valley Center Pub Sch | Sedgwick | New District Office | 1653286 | 1653286 | 09-16-2009 | 07-31-2010
| Valley Center Pub Sch | Sedgwick | New Transportation Facility | 2208442 | 2208442 | 11-19-2009 | 10-31-2010
| Valley Center Pub Sch | Sedgwick | Roof/HVAC | 865500 |  | 08-23-2010
| Valley Center Pub Sch | Sedgwick | 5th/6th Grade Rennovation | 25000 |  | 06-14-2011
| Valley Center Pub Sch | Sedgwick | 7th/8th Grade Rennovation | 787593 |  | 06-14-2011
|  |  | Total for D0262 | 58419616 | 7399930
D0307 | Ell-Saline | Saline | Ell-Saline Schools | 6815000 |  | 07-01-2009
|  |  | Total for D0307 | 6815000
D0348 | Baldwin City | Douglas | Baldwin Primary Center | 13270536 |  | 08-01-2009
| Baldwin City | Douglas | Performing Arts Center | 4741858 |  | 04-01-2010
|  |  | Total for D0348 | 18012394
D0365 | Garnett | Anderson | New Elementary School Construction | 14485000 |  | 01-01-2011
|  |  | Total for D0365 | 14485000
D0376 | Sterling | Rice | New Grade School | 8587591 |  | 06-10-2009
| Sterling | Rice | High School Addition/Remodel | 10209691 |  | 09-01-2010
|  |  | Total for D0376 | 18797282
D0383 | Manhattan-Ogden | Riley | Ogden | 4674602 | 3415884 | 11-23-2009 | 10-01-2010
| Manhattan-Ogden | Riley | Amanda Arnold | 4350354 | 4199358 | 12-18-2009 | 10-31-2010
| Manhattan-Ogden | Riley | Manhattan High West | 42407164 |  | 03-09-2010
| Manhattan-Ogden | Riley | Lee | 10508994 |  | 06-01-2010
| Manhattan-Ogden | Riley | Northview | 8663712 |  | 06-28-2010
| Manhattan-Ogden | Riley | Woodrow Wilson | 4360841 |  | 02-11-2011
| Manhattan-Ogden | Riley | Theodore Roosevelt | 4674893 |  | 04-05-2011
| Manhattan-Ogden | Riley | Marlatt | 8036964 |  | 05-31-2011
| Manhattan-Ogden | Riley | Bluemont | 4709472 |  | 06-15-2011
|  |  | Total for D0383 | 92386996 | 7615242
D0402 | Augusta | Butler | Ewalt Elementary Remodel/Addition | 3675364 | 3124661 | 03-01-2009 | 07-31-2010
| Augusta | Butler | AHS PH I & Press Box | 2953600 | 2741471 | 05-11-2009 | 07-01-2010
| Augusta | Butler | AHS Phase II | 6500590 |  | 02-01-2010
| Augusta | Butler | Lincoln Elementary Building | 11093428 |  | 06-01-2010
| Augusta | Butler | Robinson Elementary Addition & Remodel | 5332780 |  | 11-08-2010
| Augusta | Butler | AMS Phase I | 670298 |  | 05-25-2011
| Augusta | Butler | Garfield Elementary Building | 10600808 |  | 06-01-2011
|  |  | Total for D0402 | 40826868 | 5866132
D0432 | Victoria | Ellis | High School Addition | 2696561 |  | 10-19-2009
|  |  | Total for D0432 | 2696561
D0437 | Auburn Washburn | Shawnee | MS Remodel | 4758134 | 4758134 | 11-06-2008 | 07-01-2010
| Auburn Washburn | Shawnee | Pauline Central Remodel | 1776954 | 1776954 | 03-24-2009 | 08-01-2010
| Auburn Washburn | Shawnee | HS Balcony & Cafeteria Remodel | 3431219 | 3431219 | 03-16-2010 | 09-17-2010
| Auburn Washburn | Shawnee | HS Football turf | 858030 | 858030 | 06-09-2010 | 09-01-2010
|  |  | Total for D0437 | 10824337 | 10824337
D0446 | Independence | Montgomery | Independence Intermediate School | 14900000 |  | 11-20-2009
| Independence | Montgomery | Independence Middle School | 13200000 |  | 03-15-2010
| Independence | Montgomery | Independence High School | 17000000 |  | 04-15-2010
|  |  | Total for D0446 | 45100000
D0467 | Leoti | Wichita | Wichita County Elementary | 4500000 |  | 07-01-2010
|  |  | Total for D0467 | 4500000
D0473 | Chapman | Dickinson | New Schools due to Tornado | 8200000 |  | 07-01-2009
|  |  | Total for D0473 | 8200000
D0476 | Copeland | Gray | New building classrooms and gym | 4000000 | 4166513 | 10-28-2008 | 08-31-2010
|  |  | Total for D0476 | 4000000 | 4166513
D0487 | Herington | Dickinson | Herington Elementary/Track & Field | 14900000 | 15942812 | 07-01-2010 | 06-30-2011
|  |  | Total for D0487 | 14900000 | 15942812
D0490 | El Dorado | Butler | Skelly Elementary | 14910000 |  | 05-01-2011
| El Dorado | Butler | El Dorado Middle School | 20600000 |  | 05-01-2011
|  |  | Total for D0490 | 35510000
D0491 | Eudora | Douglas | 2007 Bond Issue Construction Projects | 45000000 | 46000000 | 01-01-2008 | 01-31-2011
|  |  | Total for D0491 | 45000000 | 46000000
D0497 | Lawrence | Douglas | Technology | 8900000 | 8917906 | 07-01-2006 | 06-30-2011
|  |  | Total for D0497 | 8900000 | 8917906
|  |  | GRAND TOTALS | 613174369 | 284598725